MEETING DOCUMENT

**Task Group Management (TG-M 20-2)**

14 May 2020

Virtua meeting

**Agenda Item: 4. TG-M Workplan**

**Subject: Work Plan TG-M 2020**

**Document No.:** TG-M 20-2/4rev

**Date:** 14 May 20

**Submitted by: Chair TG-M/CWSS**

This document contains the Work Plan 2020 of the Task Group Management (TG-M), including responsibilities arising from TG-M 19-2 and preliminary meeting TG-M in 2020, as well as by the development of the Single Integrated Management Plan (SIMP). The work plan is considered a living document.

**Proposal:** The group is invited to adopt the work plan 2020.

ANNEX 1: Work Plan 2020 Task Group Management (TG-M)

Table: Work plan 2020 of the Task Group Management (TG-M) with deliverables/products of the group´s responsibility in black, and supervision and coordination activities in grey. Items in brackets are temporary dealt with in TG-M but will need further allocation within the TWSC (e.g., Partnership Hub).

| L**eeuwarden Declaration** | **TG-M role** | **Products 2020 (what)** | **Responsible group/body/person (who)** | **Time schedule incl. milestones (when)** |
| --- | --- | --- | --- | --- |
| 3. Single integrated management plan (SIMP) | Support and contribute | First final draft of the complete SIMP | TG-WH, CWSS (SIMP officer) | 2020-11 |
| 3a Tourism | None | Content on chosen SIMP key topic headings | NG-ST leads, Support managers and TG-MA | TBD by NG-ST |
| 3b. Fisheries | Responsible | Proposal working approach | TG-M | 2020-03 (TG-M 20-1) |
| Content on SIMP key topic headings “Inventory” and “Common ground" | TG-M and fisheries specialists (potential Task Group or Round Table) | 2020-03 Basic info  2020-05 First draft (to TG-WH)  2020-09 Revision |
| Content on SIMP key topic headings "Strategies and actions for management" based on "Threats and opportunities" and considering "Climate change" | TG-M and fisheries specialists (potential Task Group or Round Table). | 2020-06 to 2020-09  Workshop or meeting of fisheries specialists (potential Task Group or Round Table)  First Draft and Revision  2020-09-20 Revision |
| Overview on fish monitoring and data | Ad hoc WG SWIMWAY | DONE 2019 |
| 3c. Shipping and ports | Responsible/Support | Content on SIMP key topic headings “Inventory”, "Strategies and actions for management" based on "Threats and opportunities" and considering "Climate change" | WSF, with support from TG-M and CWSS. | TBD WSF |
| 3d. Renewable energy, Energy from Oil and Gas, (Coastal flood defence and protection) | Responsible  (Support) | Proposal working approach | TG-M/SH | 2020-03 (TG-M 20-1) |
| Content on SIMP headings “Inventory” and “Common ground | TG-M/SH, CWSS (SIMP officer) (EG-C responsible for coastal flood defence and protection) | 2020-03 Basic info  2020-04 First draft (to TG-WH 2020-04-29)  2020-09 Revision |
| Content on SIMP key topic headings "Strategies and actions for management" based on "Threats and opportunities" and considering "Climate change" | TG-M, CWSS (SIMP officer), and depending on working approach proposal. Collaboration with EG-C for climate change as appropriate.  (EG-C responsible for coastal flood defence and protection) | 2020-06 to 2020-09  Workshop or meeting depending on working approach proposal  First Draft and Revision  2020-09-20 Revision |
| Monitoring, data collection and data management | TG-MA | TBD TG-MA |
| 5. Wadden Sea Flyway Initiative (WSFI) | Observe | Arctic Cooperation | WSFI SG | 2020-11 |
| Observe | Monitoring of key sites along Flyway | 2020-02, on-going |
| Observe | Capacity Building | On-going |
| 12. Breeding Bird Action Plan | Oversee[[1]](#footnote-1) | Breeding bird trend report | EG-MB/BB | 2020-08 |
| 13. SWIMWAY | Observe/  support | Implementation SWIMWAY Vison | TG-M/ad hoc WG SWIMWAY |  |
| Observe/  support | ToR and work programme for EG Fish | 2020-11 |
| 14. Management & Wardening | Responsible | (Site) Managers Workshop | TG-M |  |
| Responsible | Wardening Workshop | TBD (to account for COVID 19) |
| 15. Seal Management Plan 2018-2022 | Evaluate and support | SMP and Annual Reporting | EG-Seals |  |
| Oversee | Annual Reporting on harbour seal and grey seal population | 2020-07 and -11 |
| 16. Harbour porpoises | Observe and evaluate | Inclusion to ToR of EG-Seals | EG-Seals | 2020-11 |
| 17. Alien Species (MAPAS) | Oversee | Implementation MAPAS / Alien Species Platform | EG-AS | 2020-11 (on-going) |
| 20. Quality Status Report | Support | Draft Proposal for next QSR (joint note TG-MA TG-M) | TG-MA | TBD TG-MA |
| 21. Sustainable fisheries | Responsible | Inventory/Framework for sustainable fisheries | TG-M/CWSS | 2020-05 for WSB 31 (compare SIMP 3b) |
| 22.-23 Marine litter | Responsible/Support if needed/Ignition phase | Inventory on activities | [TG-M] NL/D/QSR thematic report authors/ TG-WH | 2020-xx for WSB 32 |
| [24. Light emissions] | Support | Inventory on activities | WSF/Partnership Hub |  |
| 29. Renewable energy and its transportation | Responsible | Overview on concepts for renewable energy transport/sea floor /(Inventory study 2020) | TG-M (DK, D, NL, coordination by ?) | TBD (compare SIMP 3d) |
| [30.-34. Sustainable –Shipping and Ports] | Responsible | Concept on Awareness and Education | TG-M | TBD (compare SIMP 3c) |
| Support | WSF Round table approach | [WSF in collaboration with TG-M] | TBD (compare SIMP 3c) |
| 36. Joint Program on Research | Support | Installation of T Programming Committee on Wadden Sea Research | TRA-RMC | TBD by TRA-RMC/WSB |
| 42. Review progress made on LD | Responsible | Review Progress | TG-M/CWSS | 2020-11 WSB 32 |
| 44. 15th International Scientific Wadden Sea Symposium | Support | Establishment of planning committee and organisation | Schleswig-Holstein | 2021-03-23 to 2021-03-26 |
| Wadden Sea Plan (WSP) | Supervise | Implementation of WSP/Towards technical update of WSP | [TG-M] | On-going |

1. Oversee: Processes and products are followed and aligned to trilateral policy and coordinated where necessary [↑](#footnote-ref-1)